Mino Bimaadiziwin Partnership meeting for March 14, 2022

Date: 	Mar 14, 2022, 03:00 PM Central Time (US and Canada)

Attendees: Shirley Thompson (facilitator), Tanzim Ahmed, Kimlee Wong, Lancelot Coar, Marleny Bonnycastle, Keshab Thapa, Alaba Awos, Stewart Hill, Misbah Khaliq, Myrle Ballard, Angela Dumas, Noam Gonick, Ajarat Adegun, Folarin Solademi, Chima Onyeneke, Panos Polyzois

March Meeting Notes:

| Topics | Items of Discussion & Notes | Action/ Motion | Person/People Responsible |
| --- | --- | --- | --- |
| - Approve minutes from last meeting | - Review of minutes from last meeting on Feb.7, 2022. | Minutes 1st- Marleny B. 2nd – Myrle. B. | Unanimous for minutes & agenda |
| - Agenda | - Approval of agenda | 1st. – Shauna 2nd - Folarin |  |
| - Architecture students trailer and designs | - Will post updates on Instagram and Facebook about a webinar on March 21, 2022 - Shawn and Lancelot will present in the webinar & everyone welcome - This will help to understand the design of building small homes |  | Lancelot |
| - Research Article | - Preparing article to submit on the special issue in ANSER/ARES - About six (6) articles are under review including housing articles, Indian,Act, Treaties, Lake St.Martin,training. - Myrle with Donna and Shirley received 2.5 million in funding to develop a land-based youth leadership model - Needs students to work with |  | Myrle & Stewart-Editors |
| - Land use mapping | - Total 70 interviews were conducted to develop Traditional Land use maps (40 in FWFN and 30 in Maawandoon - Digitization is going on using ArcGIS Pro - Hoping to submit a report on June for FWFN and September for Maawandoon |  | Keshab |
| - Camp Kitigay Ecosystem Restoration Camp | - Ecosystem Restoration Camp started - Planning a tour on April 28th, 2022 - From learning about 40 such camps in the world, collecting ideas for future Kitigay process - Planning 1 to 2 events/ workshops in the summer |  | Noam Angela |
| - Adjourn |  |  |  |